## Launch plan
LedgerPoint launch plan
Assessment date | 2026-10-14T00:00:00.000Z |  | Plan status | Draft. Scope and capacity unconfirmed.
Current position | C7 qualified in development. G4 complete. G5–G7 pending.
Plan start (Monday) | 2026-10-19T00:00:00.000Z |  | Candidate | Exact C7 qualified. Composite app unqualified.
Focused delivery days per week | 5 |  | G4 | Verified complete
Pilot delay / fix allowance (days) | 10 |  | G5–G7 | Pending owner decisions and execution
Pilot observation (calendar weeks) | 4 |  | Main PR approvals | Temporary zero-review window open
Public delay / fix allowance (days) | 5 |  | Closure | Two-approval restoration approved; unapplied
Forecasts assume one sequential build/review workstream and five focused delivery days a week. This is not measured velocity.
Milestone / effort | Low estimate | Base estimate | High estimate | Definition
Pilot work (delivery days) | 47 | 77 | 136 | One shared estimate per workstream; 70 feature rows are not added together.
Public extra work (delivery days) | 7 | 15 | 27 | Feedback fixes, commercial readiness and final acceptance after pilot observation.
Private pilot target | 2027-01-11 | 2027-02-22 | 2027-05-17 | Forecast Monday after estimated pilot work and allowance. All pilot acceptance gates must pass.
Public release target | 2027-03-01 | 2027-04-19 | 2027-08-02 | Adds observation weeks, public work and public allowance. Not a committed or approved release.
Forecast confidence | Low until scope, capacity and accepted end-to-end delivery are confirmed.
Weekly view coverage | 52-week view covers the base target
Immediate owner decision | G5: exact PR26 acceptance and one ordinary merge. This plan does not grant that approval.
Next planning checkpoint | Reforecast after the first accepted invoice-to-ledger-to-report journey and two weekly delivery reviews.
Finding | Issue | State | Workstream | Required response
B01 | Posting succeeds without accounting effect | Release blocker | W05 | Invoice/bill status updates and journal-generation success response do not call canonical posting.
B02 | Financial reports use incompatible legacy data | Release blocker | W09 | Schema-shaped report probes returned zero P&L/TB totals; string-money inputs produced NaN or concatenated totals. Reports also load legacy entities.
B03 | Financial and role inputs remain broadly writable | Release blocker | W03 | Membership role input is not allowlisted; generic entity writes accept broad invoice fields and mainly reject read_only.
B04 | VAT approval can use persisted stale evidence | Release blocker | W08 | Source/context revalidation is not performed in approveVATReturn transaction.
B05 | Full customer journeys and production recovery unverified | Evidence gap | W13 / W14 | Current assessment contains static review and in-memory probes, not authenticated business journeys, database promotion or a production restore.
B06 | Durable upload and provider integration incomplete | Scope / implementation gap | W10 / D02 | Compatibility upload, extraction and email methods are stubs; other actual AI services exist. Provider choices remain explicit.
Decision | Subject | Owner | State | Decision needed
D01 | Pilot scope and exclusions | Lee | Pending | Confirm private pilot versus public first; approved UK/GBP core scope retained. Extra contacts/items/quotes/orders/live banking/HMRC filing remain separate choices.
D02 | Providers and optional automation | Lee | Pending | Confirm durable storage and invoice delivery boundary. Choose whether OCR/email/notifications/recurring generation are launch requirements before adding estimates.
D03 | Delivery capacity | Lee | Pending | Default model assumes five focused delivery days per week across the named build/review work, not five days of owner availability. Replace with observed capacity.
D04 | G5 exact PR acceptance and ordinary merge | Lee | Pending | PR26 remains draft at exact A/B. Current request authorizes assessment/planning only; acceptance and merge are a separate concrete decision.
D05 | G6 exact activated run and normal Environment release | Lee | Pending | Actual merged G does not yet exist. Fresh exact-G/C7 preflight and one specific run/release decision are required.
D06 | G7 result acceptance and exception closure | Lee | Pending | Accept new activated evidence and execute the already approved closure at its applicable condition; preserve historical candidate evidence.
D07 | Pilot data and opening-balance cohort | Lee + accounting reviewer TBD | Pending | Choose new companies or reviewed opening balances. Existing-business historical migration is not silently included.
D08 | Production, accounting, security and release reviewers | Lee | Pending | Name review owners and accept release evidence. The bounded development owner exception does not approve production release.
Weekly update | Change owners, status, approvals and acceptance in Workstreams. Change forecast drivers above.
Review boundary |  |  |  | Exact workspace source plus pure synthetic probes. Live customer, database and deployment journeys remain unverified.
Formulas:
Low estimate = IF(OR(COUNT(B9:B12)<>4,B9<=0),"Inputs needed",IF(AND(ISNUMBER([Low estimate, row above]),ISNUMBER(B18)),[Low estimate, row above]+7*B11+7*CEILING((B18+B12)/B9,1),"Estimate needed"))
Base estimate = IF(OR(COUNT(B9:B12)<>4,B9<=0),"Inputs needed",IF(AND(ISNUMBER([Base estimate, row above]),ISNUMBER(C18)),[Base estimate, row above]+7*B11+7*CEILING((C18+B12)/B9,1),"Estimate needed"))
Plan status = IF(OR(COUNT(B9:B12)<>4,B9<=0),"Inputs needed",IF(AND(ISNUMBER([Plan status, row above]),ISNUMBER(D18)),[Plan status, row above]+7*B11+7*CEILING((D18+B12)/B9,1),"Estimate needed"))

## Workstreams
Remaining workstreams
Keep W01–W18 order. Filtering is safe. Owners and estimates are proposed; pending execution approvals remain separate.
ID | Workstream | Stage | Proposed owner | Acceptance owner | Low days | Base days | High days | Depends on | Status | Approval | Acceptance | Start week | Finish week | Complete when | Review state
W01 | Confirm pilot scope, capacity and release reviews | Pilot | Lee | Lee | 1 | 1 | 2 |  | Not started | Pending | Not verified | 2026-10-19 | 2026-10-19 | Named pilot scope, working capacity, exclusions and review owners recorded. G1 development exception is not production authority. | Awaiting approval
W02 | Complete G5–G7 development activation and closure | Pilot | Replit + Codex | Lee | 1 | 2 | 5 | W01 | Not started | Pending | Not verified | 2026-10-19 | 2026-10-19 | Accept exact PR26 A/B, separately authorize ordinary merge and one exact-G qualification/release, verify results, accept and apply the approved closure when triggered. | Awaiting approval
W03 | Roles, write contracts and server money calculations | Pilot | Replit + Codex | Lee + security reviewer TBD | 5 | 8 | 13 | W02 | Not started | Pending | Not verified | 2026-10-19 | 2026-11-02 | Unknown roles/fields, revoked/cross-company access and crafted totals are rejected. Server money/rounding and typed error contracts pass authenticated HTTP tests. | Awaiting approval
W04 | Posting providers, accounts, configuration and periods | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 5 | 8 | 14 | W03 | Not started | Pending | Not verified | 2026-11-02 | 2026-11-09 | Production-capable transaction-bound source/context providers, protected account mappings, fiscal periods and controlled close/reopen pass safety and configuration tests. | Awaiting approval
W05 | Canonical invoice and bill lifecycle | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 3 | 5 | 9 | W04 | Not started | Pending | Not verified | 2026-11-09 | 2026-11-16 | Create, approve and post both source types with balanced AR/AP/revenue/cost/VAT, source freshness, idempotency, immutability and explicit failure states. | Awaiting approval
W06 | Payments, allocation, credits, refunds and statements | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 4 | 7 | 12 | W05 | Not started | Pending | Not verified | 2026-11-16 | 2026-11-30 | Partial/split/excess payments, allocation/reversal, credits/refunds and statements reconcile to journals with no duplicate cash effect. | Awaiting approval
W07 | CSV banking, categorisation, transfers and reconciliation | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 4 | 6 | 11 | W06 | Not started | Pending | Not verified | 2026-11-30 | 2026-12-07 | Import replay and recovery are safe; approved categories, transfers and matches generate correct single accounting effects with zero transfer income/expense/VAT. | Awaiting approval
W08 | VAT freshness, evidence and preparation/export | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 3 | 5 | 9 | W07 | Not started | Pending | Not verified | 2026-12-07 | 2026-12-14 | Standard invoice-basis VAT boxes reconcile; concurrent source changes reject stale approval; versioned evidence/export is complete and labelled prepared/exported. | Awaiting approval
W09 | Canonical financial reports, aging and export parity | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 4 | 7 | 12 | W08 | Not started | Pending | Not verified | 2026-12-14 | 2026-12-21 | P&L, Balance Sheet, Trial Balance, GL and AR/AP aging reconcile to posted journals. Schema-shape, decimal strings, dates, pagination and export fixtures pass. | Awaiting approval
W10 | Durable documents and issued invoice copies | Pilot | Replit + Codex | Lee | 2 | 4 | 7 | W09 | Not started | Pending | Not verified | 2026-12-21 | 2026-12-28 | Approved storage/document-access design, durable issued PDF copies and safe upload/failure handling verified. OCR/provider email additions need scope review. | Awaiting approval
W11 | Onboarding, Ask, core workspaces and recovery UX | Pilot | Replit + Codex | Lee | 3 | 5 | 9 | W10 | Not started | Pending | Not verified | 2026-12-28 | 2027-01-04 | An invited business can set up and complete all pilot workflows on desktop/mobile with company-safe Ask, clear errors, loading/empty states and no misleading placeholders. | Awaiting approval
W12 | Pilot cohort, opening balances and data boundary | Pilot | Replit + Codex | Lee + accounting reviewer TBD | 2 | 3 | 6 | W11 | Not started | Pending | Not verified | 2027-01-04 | 2027-01-11 | New-company or reviewed opening-balance cohort chosen, reconciled and recoverable. Any historical migration requires its own evidence, plan and approval. | Awaiting approval
W13 | Full journeys, financial regressions and release security | Pilot | Replit + Codex | Lee + reviewers TBD | 5 | 8 | 13 | W12 | Not started | Pending | Not verified | 2027-01-11 | 2027-01-18 | Synthetic end-to-end invoice/bill/payment/ledger/VAT/report journeys, concurrency, role/isolation, export, accessibility and error recovery pass; blocking findings resolved. | Awaiting approval
W14 | Production configuration, recovery and monitoring | Pilot | Replit + Codex | Lee + operations/security reviewer TBD | 4 | 6 | 10 | W13 | Not started | Pending | Not verified | 2027-01-18 | 2027-01-25 | Reviewed schema/config promotion, secrets/origin/rate limits, scheduler topology, logs/alerts, isolated restore and rollback verified; production authorization remains separate. | Awaiting approval
W15 | Pilot acceptance and controlled onboarding | Pilot | Lee + invited pilot businesses | Lee | 1 | 2 | 4 | W14 | Not started | Pending | Not verified | 2027-02-01 | 2027-02-01 | Launch scope and evidence accepted; operational support and stop/recovery rules established before admitting the approved pilot cohort. | Awaiting approval
W16 | Pilot feedback fixes and operating hardening | Public | Replit + Codex | Lee + pilot reviewers | 4 | 8 | 15 | W15 | Not started | Pending | Not verified | 2027-03-22 | 2027-03-29 | Resolve pilot issues and demonstrate reliable posting, onboarding, backups, alerting and support through the observation window. | Awaiting approval
W17 | Public onboarding, support and commercial launch checks | Public | Lee + Replit/Codex | Lee | 2 | 4 | 7 | W16 | Not started | Pending | Not verified | 2027-03-29 | 2027-04-05 | Agree pricing/access/support and applicable terms/privacy review; capacity and public onboarding are tested. Automated billing/provider additions need separate scope estimates. | Awaiting approval
W18 | Public release acceptance | Public | Lee + release reviewers TBD | Lee | 1 | 3 | 5 | W17 | Not started | Pending | Not verified | 2027-04-05 | 2027-04-05 | Final customer journeys and operational checks accepted, remaining launch blockers closed and a separately authorized release decision recorded. | Awaiting approval
Formulas:
Start week = IF(AND('Launch plan'!$B9>0,ISNUMBER('Launch plan'!$B8),COUNT(G7:[Base days])=1),'Launch plan'!$B8+7*INT(0/'Launch plan'!$B9),"Inputs needed")
Start week = IF(AND('Launch plan'!$B9>0,ISNUMBER('Launch plan'!$B8),COUNT(G7:[Base days])=2),'Launch plan'!$B8+7*INT(SUM(G7:[Base days, row above])/'Launch plan'!$B9),"Inputs needed")
Finish week = IF(AND('Launch plan'!$B9>0,ISNUMBER('Launch plan'!$B8),COUNT(G7:[Base days])=1),MAX([Start week],'Launch plan'!$B8+7*(CEILING(SUM(G7:[Base days])/'Launch plan'!$B9,1)-1)),"Inputs needed")
Finish week = IF(AND('Launch plan'!$B9>0,ISNUMBER(('Launch plan'!$C20+7*'Launch plan'!$B11)),COUNT(G22:[Base days])=1),MAX([Start week],('Launch plan'!$C20+7*'Launch plan'!$B11)+7*(CEILING(SUM(G22:[Base days])/'Launch plan'!$B9,1)-1)),"Inputs needed")

## Weekly schedule
Base weekly schedule
Forecast work only. Pending approvals and acceptance remain visible in Workstreams. Read each task’s completion evidence there.
ID | Workstream | Proposed owner | Review state | time axis 2026-10-19 to 2027-10-11
W01 | Confirm pilot scope, capacity and release reviews | Lee | Awaiting approval | 2026-10-19: Plan
W02 | Complete G5–G7 development activation and closure | Replit + Codex | Awaiting approval | 2026-10-19: Plan
W03 | Roles, write contracts and server money calculations | Replit + Codex | Awaiting approval | 2026-10-19: Plan; 2026-10-26: Plan; 2026-11-02: Plan
W04 | Posting providers, accounts, configuration and periods | Replit + Codex | Awaiting approval | 2026-11-02: Plan; 2026-11-09: Plan
W05 | Canonical invoice and bill lifecycle | Replit + Codex | Awaiting approval | 2026-11-09: Plan; 2026-11-16: Plan
W06 | Payments, allocation, credits, refunds and statements | Replit + Codex | Awaiting approval | 2026-11-16: Plan; 2026-11-23: Plan; 2026-11-30: Plan
W07 | CSV banking, categorisation, transfers and reconciliation | Replit + Codex | Awaiting approval | 2026-11-30: Plan; 2026-12-07: Plan
W08 | VAT freshness, evidence and preparation/export | Replit + Codex | Awaiting approval | 2026-12-07: Plan; 2026-12-14: Plan
W09 | Canonical financial reports, aging and export parity | Replit + Codex | Awaiting approval | 2026-12-14: Plan; 2026-12-21: Plan
W10 | Durable documents and issued invoice copies | Replit + Codex | Awaiting approval | 2026-12-21: Plan; 2026-12-28: Plan
W11 | Onboarding, Ask, core workspaces and recovery UX | Replit + Codex | Awaiting approval | 2026-12-28: Plan; 2027-01-04: Plan
W12 | Pilot cohort, opening balances and data boundary | Replit + Codex | Awaiting approval | 2027-01-04: Plan; 2027-01-11: Plan
W13 | Full journeys, financial regressions and release security | Replit + Codex | Awaiting approval | 2027-01-11: Plan; 2027-01-18: Plan
W14 | Production configuration, recovery and monitoring | Replit + Codex | Awaiting approval | 2027-01-18: Plan; 2027-01-25: Plan
W15 | Pilot acceptance and controlled onboarding | Lee + invited pilot businesses | Awaiting approval | 2027-02-01: Plan
W16 | Pilot feedback fixes and operating hardening | Replit + Codex | Awaiting approval | 2027-03-22: Plan; 2027-03-29: Plan
W17 | Public onboarding, support and commercial launch checks | Lee + Replit/Codex | Awaiting approval | 2027-03-29: Plan; 2027-04-05: Plan
W18 | Public release acceptance | Lee + release reviewers TBD | Awaiting approval | 2027-04-05: Plan
BUF1 | Pilot decision / fix allowance |  |  | 2027-02-08: Allowance; 2027-02-15: Allowance
PILOT | Pilot observation |  |  | 2027-02-22: Observe; 2027-03-01: Observe; 2027-03-08: Observe; 2027-03-15: Observe
BUF2 | Public decision / fix allowance |  |  | 2027-04-12: Allowance
START | Private pilot target |  |  | 2027-02-22: Pilot
START | Public release target |  |  | 2027-04-19: Public

## Features
70-area feature assessment
Static source findings. Customer-release acceptance is unverified. Pilot inclusion and deferral are proposals until Lee confirms scope.
ID | Area | Pilot scope | Current assessment | What exists now | Remaining acceptance requirement | Workstream | Customer acceptance | Prior matrix status | Source
1 | Authentication & onboarding | Included proposal | Partial | Clerk auth, protected routes and setup wizard exist. | Prove sign-up, recovery, first-company setup, resume and role-specific journeys. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/AuthContext.jsx
2 | Company management | Included proposal | Partial | Company routes now use active-membership guards. Earlier inactive-member defect label is stale. | Validate company fields and archive/delete lifecycle; prove every company-management route rejects revoked access. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/companies.ts
3 | Users, teams and permissions | Included proposal | Partial | Active-membership checks exist; membership routes still accept arbitrary role strings and generic writes mainly block read_only. | Enforce approved roles/capabilities, validate role changes and test the full API/UI role matrix. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/companies.ts
4 | Dashboard | Included proposal | Partial | Dashboard and widgets exist, drawing from operational records. | Define each metric, derive financial values from accepted journals and prove drill-down parity. | W09 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Dashboard.jsx
5 | Customers | Included proposal | Partial | Customer CRUD and invoice selection exist. | Validate party contracts; reconcile customer balances/statements and complete the core workspace/Ask journey. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Customers.jsx
6 | Suppliers | Included proposal | Partial | Supplier CRUD and bill selection exist. | Validate party contracts; reconcile supplier balances/statements and complete the core workspace/Ask journey. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Suppliers.jsx
7 | Contacts | Scope decision | No dedicated workflow | No independent Contact entity is in the inspected entity map. | Decide whether a separate module is needed; party contact fields can remain the proposed pilot boundary. | D01 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/entities.ts
8 | Sales invoices | Included proposal | Blocked integration | Invoice form saves records; postSalesInvoice updates status only. Journal-generation handler returns success without generating a journal. | Use server-calculated money, immutable posting, current source/context controls and canonical AR/revenue/VAT journals; reject false success. | W05 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
9 | Credit notes | Included proposal | Partial | Sales and supplier credit-note forms/registers exist. | Add canonical posting, allocation, controlled corrections/refunds and VAT/audit consequences. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/SalesCreditNoteForm.jsx
10 | Quotes/estimates | Scope decision | No dedicated workflow | No Quote entity is in the inspected entity map. | Defer unless explicitly added to launch scope; do not count an unapproved quote feature as a release blocker. | D01 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/entities.ts
11 | Purchase bills | Included proposal | Blocked integration | Bill form and records exist; postPurchaseBill updates status without canonical posting. | Implement the approved draft/approval/posting lifecycle with AP/cost/VAT journals and immutability. | W05 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
12 | Purchase orders | Scope decision | No dedicated workflow | No PurchaseOrder entity is in the inspected entity map. | Defer unless separately approved; define order-to-bill semantics before implementation. | D01 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/entities.ts
13 | Products/services/items | Scope decision | No dedicated workflow | No separate item catalogue is in the inspected entity map. | Decide whether validated invoice/bill line items suffice for the pilot; a catalogue is a separate scope choice. | D01 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/entities.ts
14 | Bank accounts | Included proposal | Partial | Manual bank account records and transaction views exist; live banking is labelled coming soon. | Validate manual/CSV account controls and reconcile balances. Live feeds are excluded from the proposed pilot. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/BankAccounts.jsx
15 | Bank transaction importing | Included proposal | Partial | CSV import UI and dedicated initial bank-entry handlers exist. | Prove malformed-file recovery, duplicate/replay behavior, safe mapping, complete import audit and company isolation. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/bank_transactions/ImportCSVDialog.jsx
16 | Bank transaction management | Included proposal | Partial | Registers and dedicated bank-entry/classification routes exist; matched-state generic writes are restricted. | Validate every bank mutation and bulk operation; prove concurrent changes cannot bypass reconciliation. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
17 | Transaction categorisation | Included proposal | Blocked integration | Categorisation suggestions/services exist; canonical category-to-ledger workflow is not connected. | Explicit approval must produce one balanced journal with correct tax, source and report effects. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/categorise.ts
18 | Bank reconciliation | Included proposal | Blocked integration | Matching and transactional approval code exist. Earlier phase-scoped completion does not establish ledger/cash effects. | Link approval to canonical payments/journals atomically; prove partial, multiple, stale, duplicate and cross-company cases. | W07 | Unverified | A* | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/approval.ts
19 | Transfers | Included proposal | Partial | recordBankTransfer now creates a paired opposite bank row with amount/company checks. Earlier detection-only label is stale. | Add canonical movement/audit, deterministic replay protection and prove zero income/expense/VAT effect. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
20 | Recurring transactions | Defer proposal | Detection only | Recurrence detection exists; no complete recurring draft-generation lifecycle was found. | Keep detection in the pilot if useful; templates/schedules need a separate approved scope and idempotency contract. | D02 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/detectors.ts
21 | Chart of accounts | Included proposal | Partial | Chart UI, account records and UK default-account creation exist. | Control account classifications, protected mappings/defaults and effective configuration; integrate canonical posting/reporting. | W04 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/ChartOfAccounts.jsx
22 | Accounting configuration | Included proposal | Partial | Company/accounting settings fragments exist. | Implement validated numbering, mappings, fiscal setup and posting-context configuration without rewriting history. | W04 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Settings.jsx
23 | VAT configuration | Included proposal | Partial | VAT rules/profile and deterministic Standard scheme services exist; supported launch scheme is already decided. | Enforce the approved Standard invoice-basis scope, effective versions and unsupported-treatment rejection. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/vat.ts
24 | VAT calculations | Included proposal | Partial | Deterministic VAT calculation and scenario tests exist. | Prove journal/source authority, integer-money/rounding invariants and supported treatment coverage through the full journey. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/vatMath.ts
25 | VAT returns | Included proposal | Partial | Draft, refresh, revision and review return services exist. | Complete the approved preparation/export lifecycle and recovery with reconciled posted evidence; no direct HMRC filing. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/vat.ts
26 | VAT review/approval/locking | Included proposal | Release blocker | approveVATReturn checks exceptions then locks the persisted return; source revalidation is not performed in that transaction. | A concurrent source/context change must prevent locking stale VAT evidence; test mutation races and capability checks. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/vat.ts
27 | VAT evidence and drill-downs | Included proposal | Partial | VAT box drill-down component and evidence/review data exist. | Reconcile each box to authoritative posted evidence and produce a complete, versioned export pack. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/vat_returns/VATBoxDrillDown.jsx
28 | Collections | Included proposal | Partial | Collections analysis, draft approval, email-app handoff and manual sent recording exist. Provider delivery is not established. | Reconcile overdue amounts to the accepted ledger; make manual handoff and delivery status clear and audited. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/collections/ReminderDraftDialog.jsx
29 | Payments | Included proposal | Blocked integration | updatePaymentStatus updates document balances under locks without canonical payment journals. | Implement payment records, allocation/reversal, partial/split/excess handling and cash/AR/AP journals with replay safety. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
30 | Customer balances | Included proposal | Partial | Customer views use invoice paid/balance fields. | Rebuild authoritative party balances/statements from canonical payments/allocations and reconcile to journals. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Customers.jsx
31 | Supplier balances | Included proposal | Partial | Supplier views use bill paid/balance fields. | Rebuild authoritative party balances/statements from canonical payments/allocations and reconcile to journals. | W06 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Suppliers.jsx
32 | Accounts receivable | Included proposal | Partial | Invoices and collections provide an operational receivables view. | Deliver reconciled AR open items, allocations, statements and aging with source drill-down. | W09 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/collections.ts
33 | Accounts payable | Included proposal | Partial | Bill register and supplier records exist. | Deliver reconciled AP open items, allocations, statements and aging; payment-run automation is a separate scope choice. | W09 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Bills.jsx
34 | Journals | Included proposal | Blocked integration | Exact C7 canonical service is qualified in isolation; the product still exposes legacy journal workflows. | Connect accepted domain commands/providers, retain database safety and prove customer journal/reversal/correction journeys. | W04 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/accounting/canonicalPosting.ts
35 | Adjustments | Included proposal | Partial | VAT adjustments exist; canonical service supports additive reversal/correction, but a complete product adjustment workflow is unproven. | Define bounded authorized adjustment UI/commands and period, audit, linkage and approval behavior. | W06 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/accounting/canonicalPosting.ts
36 | Periods/financial years | Included proposal | No dedicated workflow | No dedicated period/fiscal-year management page or route is present in the inspected product inventory; canonical tests use context providers. | Build company fiscal periods, close/reopen controls and transaction-bound context providers under the approved policies. | W04 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/accounting/canonicalPosting.ts
37 | Accounting reports | Included proposal | Release blocker | Reports read legacy JournalEntry data. Current calculator/schema shapes disagree; synthetic probes returned zero or invalid totals. | Use a canonical reporting contract, normalize money safely, include all records and prove period/export/drill-down parity. | W09 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
38 | Management reports | Included proposal | Partial | Management/dashboard widgets exist. | Validate essential pilot metrics; advanced saved comparisons/management views require scope confirmation. | W09 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Dashboard.jsx
39 | Profit & Loss | Included proposal | Release blocker | P&L calculation and selector exist. API/schema-shaped synthetic input returned income 0 instead of 200. | Wire canonical posted lines/account classifications and reconcile P&L to the ledger with period/correction fixtures. | W09 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
40 | Balance Sheet | Included proposal | Blocked integration | Balance Sheet calculation and selector exist. Earlier missing-screen label is stale; canonical authority is still absent. | Reconcile assets, liabilities, equity and current earnings as-of the chosen date to canonical journals. | W09 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
41 | Trial Balance | Included proposal | Release blocker | Trial-balance function exists, but is absent from the current report selector. Schema-shaped fixture produced debit 0 instead of 200. | Expose the approved report and reconcile canonical debit/credit totals with complete pagination and safe numeric conversion. | W09 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/reports/ReportSelector.jsx
42 | General Ledger | Included proposal | Blocked integration | General Ledger UI still reads the legacy JournalEntry entity. | Display canonical lines and source/audit drill-down with controlled periods and complete pagination. | W09 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/GeneralLedger.jsx
43 | VAT reports | Included proposal | Partial | VAT UI and legacy VAT summary exist. | Generate reconciled box/evidence reports from the accepted VAT authority and prove export parity. | W08 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/VATReturnDetail.jsx
44 | Aged debtors | Included proposal | Partial | Aged-debtor calculator/selector and collections views exist. | Derive aging from accepted open items/allocations, preserving date and unapplied-credit semantics. | W09 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
45 | Aged creditors | Included proposal | Partial | Aged-creditor calculator/selector exist. Earlier absent-report label is stale. | Reconcile supplier aging/open items to canonical AP and allocations with numeric-string and cutoff tests. | W09 | Unverified | F | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
46 | Cash/bank reporting | Included proposal | Release blocker | Bank reconciliation summary exists; decimal-string fixture returned NaN for a 150 net inflow. | Use accepted cash journals/bank reconciliation and safe money aggregation; verify statement/ledger parity. | W09 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
47 | Search | Included proposal | Partial | Page searches and Ask modal/provider exist. | Prove company/capability-safe discovery and opening of every pilot object; advanced fuzzy/saved search is a separate scope decision. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/ask/AskProvider.jsx
48 | Filters | Included proposal | Partial | Scalar and IN filters work in the client contract; other object operators are silently ignored. | Validate/reject unsupported filters, support required date/status queries and test search/export completeness. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/api/entities.js
49 | Exports | Included proposal | Partial | PDF/CSV/XLSX helpers and controls exist. | Export accepted report data with permission/audit, complete datasets, safe formatting and parity to the visible report. | W09 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportExports.js
50 | Document generation | Included proposal | Partial | InvoiceDocument and PDF generation exist. | Preserve issued copies, approved branding/data, document access and durable storage. Provider email is a scope decision. | W10 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/invoices/InvoiceDocument.jsx
51 | AI Accountant | Included proposal | Partial | AI review/task services and Ask provider route exist; generic compatibility integrations also contain stubs. | Validate source-grounded explanations, uncertainty, permissions and safe handoffs for the pilot; do not infer all AI is a stub. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/functions.ts
52 | AI task queue | Included proposal | Partial | Task engine, inbox, review and recommendation pages exist. | Prove task lifecycle, pagination, stale context handling and company-safe actions across pilot workflows. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/taskEngine.ts
53 | AI explanations | Included proposal | Partial | Explain service and rationale cards exist. | Bind every pilot recommendation to current evidence and expose uncertainty; test misleading/unsupported context. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/explain.ts
54 | AI approvals | Included proposal | Partial | Explicit approvals exist in reconciliation/VAT and the qualified core checks accounting capabilities. | Make product approval boundaries consistent and transactional; prove role and source-change races. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/approval.ts
55 | AI automation | Included proposal | Partial | A process-local scheduler and import-triggered analysis exist. Earlier scheduler-absent label is stale. | Keep analysis-only pilot behavior; prove no unintended writes, cancellation/deduplication and multi-instance operating policy. | W14 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/scheduler.ts
56 | Collections automation | Defer proposal | Manual handoff only | Reminder approval opens the user email app; the user can manually mark it sent. | Automated/provider sending is deferred in this draft; any later delivery must be approved, idempotent and auditable. | D02 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/collections/ReminderDraftDialog.jsx
57 | Bank automation | Included proposal | Partial | CSV import analysis, transfer and recurrence detection exist. | Prove recovery and monitoring for included analysis; live feed/provider automation is deferred in this draft. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/analysis.ts
58 | Reconciliation automation | Included proposal | Blocked integration | Batch review/approval exists; autonomous posting is not part of the proposed pilot. | Prove explicit approval creates one accepted accounting effect and rejects stale/duplicate/ambiguous matches. | W07 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/approval.ts
59 | Recurring transaction automation | Defer proposal | Detection only | Recurrence detector exists without a complete scheduled generation workflow. | Defer generated recurring transactions unless separately included and approved. | D02 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/ai-accountant/detectors.ts
60 | Notifications | Defer proposal | Placeholder | Notification settings are labelled coming soon. | Decide launch channels; pilot errors and actionable in-app states remain mandatory regardless of delivery-platform deferral. | D02 | Unverified | E | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Settings.jsx
61 | Tasks | Included proposal | Partial | AI tasks/workflow records exist; a general assignment workflow is unproven. | Complete included AI task lifecycle; general assignments/due dates/notifications require a separate scope decision. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/AIAccountantTasks.jsx
62 | Audit trail | Included proposal | Partial | Canonical audit persistence and domain VAT/reconciliation audit records exist. | Prove append-only coverage and authorized source/object history for every consequential pilot action. | W13 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/services/accounting/canonicalPosting.ts
63 | Activity history | Included proposal | Partial | Workflow activity and workspace timeline components exist. | Complete included object history/filtering and prove company isolation; broad activity views are scope-dependent. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/workspace/useWorkspaceAsk.js
64 | Company settings | Included proposal | Partial | Company/member/VAT/automation settings exist; broad company update input remains. | Apply approved capability and field contracts to all consequential settings and test historical configuration preservation. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/companies.ts
65 | User settings | Included proposal | Partial | Clerk account/profile information and settings exist. | Prove profile/recovery handoff and basic preferences; notification preferences depend on launch scope. | W11 | Unverified | C | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Settings.jsx
66 | Import/export | Included proposal | Partial | CSV bank import and selected exports exist. | Prove mapping/recovery/replay/audit and export completeness; broad legacy migration is excluded from this draft until reviewed. | W12 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/components/bank_transactions/ImportCSVDialog.jsx
67 | Error handling | Included proposal | Partial | Error handling exists but many routes return raw exception messages. | Use typed business errors, safe logging and visible recovery paths; test permission, timeout and provider failures. | W03 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/api-server/src/routes/entities.ts
68 | Empty states | Included proposal | Partial | Many pages contain empty-state UI. | Walk every pilot journey with no/partial data and provide actionable business-language guidance. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Documents.jsx
69 | Loading states | Included proposal | Partial | Page loading indicators and task state exist. | Prove cancellation, partial failure/retry and visible unavailable integrations without false success. | W11 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/pages/Reports.jsx
70 | Responsive/mobile experience | Included proposal | Unverified journeys | Responsive components exist; a current mobile/keyboard/customer regression run was not performed. | Pass desktop/tablet/mobile, keyboard/focus and error-recovery journeys for every pilot workflow. | W13 | Unverified | B | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/App.jsx

## Evidence
Evidence and review boundaries
Reviewed workspace | 085b7e0491d9adbbebcc7e8db384c575bcfa2aca
Review level | Static source assessment plus synthetic pure-function probes. No live customer/database/browser journeys run.
Source | Identity / result | What it establishes | Link
Exact workspace backup | 085b7e0491d9adbbebcc7e8db384c575bcfa2aca | Remote branch SHA read back 2026-10-14; 612 files exported for read-only assessment. | https://github.com/Future00111/ledgerpoint/tree/085b7e0491d9adbbebcc7e8db384c575bcfa2aca
PR26 activation | ead19106aaad76d604e8595337b5ab2fddda68d0 | Fresh API: draft/open/unmerged, mergeable; base 0da401737f35d68b9404982baad7405fe997636a. | https://github.com/Future00111/ledgerpoint/pull/26
Exact C7 qualification | 787d76decfa345e3c1104231e08d5ab00bc90259 | Run 38284785813 attempt 1 success. Prior independently verified 6 accounting, 18 negative and 5 cleanup checks. | https://github.com/Future00111/ledgerpoint/actions/runs/38284785813
G4 status | Verified complete 2026-10-13 | Replit dated UI addendum agrees; 2026-10-14 REST readback count0/admin/conversation controls retained. Future closure not applied. | https://github.com/Future00111/ledgerpoint/settings/branch_protection_rules/82347898
Product backlog / roadmap | Historical planning evidence | Retain original 70 feature rows; refreshed source findings replace stale implementation labels. Roadmap/PRD remain authority for scope. | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/docs/ledgerly-phase-a-j-roadmap.md
Report probes | 2 positive controls; 4 defects reproduced | Actual unmodified report function, synthetic in-memory inputs, no database/API/browser journey. | https://github.com/Future00111/ledgerpoint/blob/085b7e0491d9adbbebcc7e8db384c575bcfa2aca/artifacts/ledgerly/src/lib/reportCalculations.js
Numeric representation reference | Drizzle PostgreSQL numeric | String numeric representation is supported/default; current schema does not select number mode. Confirm actual API behavior during the customer journey tests. | https://github.com/drizzle-team/drizzle-orm/blob/main/drizzle-orm/src/pg-core/columns/numeric.ts
Probe | Expected value | Observed result
Flat numeric legacy fixture: P&L income | 200 | 200
Flat numeric legacy fixture: balanced trial balance | 200 | 200
API/schema-shaped journal headers and account_type: P&L income | 200 | 0
API/schema-shaped nested journal lines: trial balance debit | 200 | 0
Decimal strings in bank rows: cash-flow aggregation | 150 | NaN
Decimal strings in flat journal rows: trial balance debit | 200 | 00200.0000.00
Probe interpretation | Two positive controls passed. Four supplied-input report defects reproduced. No database, API, browser or posting journey was exercised.
Estimate basis | Codex planning judgments for shared remaining workstreams. Low/base/high are effort bounds, not calibrated probabilities. Owner response time and observed delivery capacity can change dates.
Release acceptance | Production readiness, migration, deployment and customer acceptance remain separate gates. The C7 single-owner exception is bounded to development activation.
Older label refreshed | Current source evidence
Company access | Active-membership guard now present; earlier unsafe-membership label is superseded for the inspected routes.
P&L / Balance Sheet / aging | Legacy calculations and report selectors exist; completion still requires correct canonical data and acceptance tests.
Trial Balance | Calculation exists, but the selector does not expose it and the schema-shaped fixture failed.
Transfers | Paired bank-entry creation now exists; canonical posting/replay acceptance remains.
AI scheduling / Ask | Process-local scheduler and a real Ask AI route exist; generic integration stubs do not establish all AI is absent.
Candidate infrastructure | C7 qualification supersedes old C2/C5 failure status; it does not qualify the composite workspace or customer journeys.